## Tasks
Project tracker
Website relaunch · update Status and % done as work moves.
Task | Owner | Start | Due | Status | % done
Collect requirements | Priya | 05 Oct 2026 | 09 Oct 2026 | Done | 100%
Design new pages | Lena | 12 Oct 2026 | 23 Oct 2026 | In progress | 60%
Write content | Tom | 19 Oct 2026 | 06 Nov 2026 | In progress | 30%
Build pages | Marcus | 26 Oct 2026 | 20 Nov 2026 | Not started | 0%
Test on phones | Aiko | 16 Nov 2026 | 25 Nov 2026 | Not started | 0%
Launch | Priya | 30 Nov 2026 | 30 Nov 2026 | Not started | 0%
Overall progress
Tasks done