PROJECT PROPOSAL

# Community Garden Network

Turning five empty lots into shared gardens by spring 2027

# Summary

We propose a network of five community gardens run by local volunteers, with a small paid coordinator. The gardens will provide fresh food, outdoor learning for two schools and a meeting place for neighbours.

# Goals

- Open five gardens with at least 120 plots in total.

- Run twelve workshops a year on growing food.

- Give 40% of plots to households on low incomes.

# Timeline

| Phase | What happens | When |
| --- | --- | --- |
| 1. Agree | Leases signed with the city; volunteers recruited | Nov – Dec 2026 |
| 2. Build | Beds, paths, water and tool sheds | Jan – Mar 2027 |
| 3. Grow | Plots assigned; first season and workshops | Apr – Oct 2027 |

# Budget

| Item | Cost |
| --- | --- |
| Materials and tools | $38,000 |
| Water connections | $12,500 |
| Coordinator (part time, 1 year) | $24,000 |
| Total | $74,500 |

# Next steps

With the council's approval at its November meeting, we can sign leases before the end of the year.